## Sheet1
Lahore Electric Supply Company Ltd (LESCO)
PROCUREMENT PLAN FOR THE YEAR 2024-25 FOR DISTRIBUTION ITEMS
1 | 2 |  | 3 |  |  | 4 | 5 | 6 | 7 | 8
Sr. No. | Name of Procurement (Description) |  | Estimated Cost |  |  | Procurement Method | Tentative date of Procurement Notice Publication | Tentative date of Award of contract | Tentative date of completion | Remarks (if any)
|  | UNIT | Qty. | Price (Rs.) | Total Cost (Mln.Rs.)
1 | 15 KVA Transformer | Nos | 120 | 255000 | 30.6 | Open competitive bidding | Sept. to Oct. 2024 | Oct. 2024 to March 2025 | Jan. 2025 to June 2025 | The Procurement will be made during financial year 2024-25
2 | 25 KVA Transformer | Nos | 1600 | 282000 | 451.2 | -do- | -do- | -do- | -do-
3 | 50 KVA Transformer | Nos | 200 | 420000 | 84 | -do- | -do- | -do- | -do-
4 | 100 KVA Transformer | Nos | 900 | 625800 | 563.22 | -do- | -do- | -do- | -do-
| 100 KVA Transformer (Rec.) | Nos | 230 | 342000 | 78.66 | -do- | -do- | -do- | -do-
5 | 200 KVA Transformer | Nos | 950 | 900000 | 855 | -do- | -do- | -do- | -do-
| 200 KVA Transformer (Rec.) | Nos | 700 | 460000 | 322 | -do- | -do- | -do- | -do-
6 | ACSR Dog Conductor | Nos | 400 | 442786 | 177.1144 | -do- | -do- | -do- | -do-
7 | ACSR Rabbit Conductor | Km | 1200 | 245670 | 294.804 | -do- | -do- | -do- | -do-
8 | ACSR Ospray Conductor | Km | 800 | 1046000 | 836.8 | -do- | -do- | -do- | -do-
9 | AAC Wasp Conductor | Km | 500 | 334500 | 167.25 | -do- | -do- | -do- | -do-
10 | AAC Ant Conductor | Km | 700 | 182000 | 127.4 | -do- | -do- | -do- | -do-
11 | Insulated Osprey Conductor | Km | 30 | 1100000 | 33 | -do- | -do- | -do- | -do-
12 | Insulated Rabbit Conductor | Km | 120 | 339000 | 40.68 | -do- | -do- | -do- | -do-
13 | Insulated Dog Conductor | Km | 20 | 482000 | 9.64 | -do- | -do- | -do- | -do-
14 | Insulated Ant Conductor | Km | 150 | 249778 | 37.4667 | -do- | -do- | -do- | -do-
15 | Insulated Wasp Conductor | Km | 250 | 482000 | 120.5 | -do- | -do- | -do- | -do-
16 | 11KV S/C Cable 500MCM | Km | 40 | 3485000 | 139.4 | -do- | -do- | -do- | -do-
17 | 15 KV XLPE 3/C 35 mm2 Cable | Km | 12 | 4750000 | 57 | -do- | -do- | -do- | -do-
18 | PVC 2/C 10mm2 (7/.052) | Km | 5000 | 130000 | 650 | -do- | -do- | -do- | -do-
19 | PVC 4/C 25mm2 (19/.052) | Km | 20 | 650000 | 13 | -do- | -do- | -do- | -do-
20 | PVC 4/C 70mm2 (19/.083) | Km | 40 | 1378000 | 55.12 | -do- | -do- | -do- | -do-
21 | PVC 4/C 120mm2 (37/.083) | Nos | 60 | 2350000 | 141 | -do- | -do- | -do- | -do-
22 | Single Phase Static Meter | Nos | 750000 | 4530 | 3397.5 | -do- | -do- | -do- | -do-
23 | 3/P AMR Smart Static Meter (with upto 20% bi-directional meter) | Nos | 70000 | 40000 | 2800 | -do- | -do- | -do- | -do-
24 | HT TOU CT/PT Operated AMR Smart Meter (with upto 20% bi-directional meter) | Nos | 350 | 40000 | 14 | -do- | -do- | -do- | -do-
25 | LT TOU CT Operated AMR Smart Meter (with upto 20% bi-directional meter) | Nos | 5500 | 40000 | 220 | -do- | -do- | -do- | -do-
26 | LT Steel Structure 30'-8" Galv. | Nos | 3000 | 43270 | 129.81 | -do- | -do- | -do- | -do-
27 | HT Steel Structure 34'-8" Galv. | Nos | 9000 | 61400 | 552.6 | -do- | -do- | -do- | -do-
28 | HT Steel Structure 45' Galv. | Nos | 1500 | 167000 | 250.5 | -do- | -do- | -do- | -do-
29 | HT Steel Structure 58' Galv. | Nos | 100 | 268505 | 26.8505 | -do- | -do- | -do- | -do-
30 | HT PC Spun Hollow Pole 36' | Nos | 9630 | 49000 | 471.87 | -do- | -do- | -do- | -do-
31 | LT PC Spun Hollow Pole 31' | Kg | 1600 | 37990 | 60.784 | -do- | -do- | -do- | -do-
32 | HT PC Spun Hollow Pole 45' | Nos | 1400 | 105440 | 147.616 | -do- | -do- | -do- | -do-
33 | T. Kit 500MCM (In door) S/C | Nos | 100 | 11000 | 1.1 | -do- | -do- | -do- | -do-
34 | T. Kit 500MCM (Out door)S/C | Nos | 300 | 15500 | 4.65 | -do- | -do- | -do- | -do-
35 | T. Kit 2AWG (Out door)3/C | Nos | 160 | 31000 | 4.96 | -do- | -do- | -do- | -do-
36 | LT Spool Insulator | Nos | 46000 | 285 | 13.11 | -do- | -do- | -do- | -do-
37 | 11 KV Pin Insulator | Nos | 32000 | 1015 | 32.48 | -do- | -do- | -do- | -do-
38 | 11 KV Disc Insulator | Nos | 32000 | 3992 | 127.744 | -do- | -do- | -do- | -do-
39 | 11 KV Steel X-Arm | Nos | 32000 | 8989 | 287.648 | -do- | -do- | -do- | -do-
40 | Steel Cross for D-Fuse | Nos | 5000 | 5290 | 26.45 | -do- | -do- | -do- | -do-
41 | 11 KV Dropout Cutout | Nos | 17000 | 26000 | 442 | -do- | -do- | -do- | -do-
42 | LT CT 800/5 Amp. | Nos | 2000 | 10050 | 20.1 | -do- | -do- | -do- | -do-
43 | LT CT 400/5 Amp. | Nos | 4000 | 10270 | 41.08 | -do- | -do- | -do- | -do-
44 | LT CT 200/5 Amp. | Nos | 4530 | 10500 | 47.565 | -do- | -do- | -do- | -do-
45 | LT CT 100/5 Amp. | Nos | 4700 | 10500 | 49.35 | -do- | -do- | -do- | -do-
46 | 11KV Shunt Capacitor 450 kvar | Nos | 300 | 274200 | 82.26 | -do- | -do- | -do- | -do-
47 | D/E Clamp ( Osp ) | Nos | 5000 | 1049 | 5.245 | -do- | -do- | -do- | -do-
48 | D/E Clamp ( Dog ) | Nos | 6000 | 586 | 3.516 | -do- | -do- | -do- | -do-
49 | Loop D/E Clamp LC-10 | Nos | 3000 | 734.272 | 2.2028 | -do- | -do- | -do- | -do-
50 | MS Box A Type 800/5A | Nos | 450 | 67690.7 | 30.4608 | -do- | -do- | -do- | -do-
51 | MS Box A Type 400/5A | Nos | 400 | 47364 | 18.9456 | -do- | -do- | -do- | -do-
52 | MS Box A Type 200/5A | Nos | 350 | 44999 | 15.7497 | -do- | -do- | -do- | -do-
53 | MS Box A Type 100/5A | Nos | 1000 | 40780 | 40.78 | -do- | -do- | -do- | -do-
54 | Anchor Shackle | Nos | 30000 | 205 | 6.15 | -do- | -do- | -do- | -do-
55 | Eye Nut | Nos | 40000 | 145 | 5.8 | -do- | -do- | -do- | -do-
56 | Insulator Pins (Steel X-Arm) | Nos | 75000 | 890 | 66.75 | -do- | -do- | -do- | -do-
57 | Stay Rod Complete | Nos | 10000 | 3938 | 39.38 | -do- | -do- | -do- | -do-
58 | Earthing Unit (Earth Rods) | Nos | 10000 | 1714 | 17.14 | -do- | -do- | -do- | -do-
59 | D-Shackle Assembly | Nos | 40000 | 297 | 11.88 | -do- | -do- | -do- | -do-
60 | Single Pole/Structure Platform | Nos | 4000 | 15250 | 61 | -do- | -do- | -do- | -do-
61 | Double Platform | Nos | 2000 | 27000 | 54 | -do- | -do- | -do- | -do-
62 | DA Bolt 12" | Nos | 3000 | 435.974 | 1.3079 | -do- | -do- | -do- | -do-
63 | DA Bolt 14" | Nos | 3000 | 435.974 | 1.3079 | -do- | -do- | -do- | -do-
64 | DA Bolt 20" | Nos | 15000 | 435.974 | 6.5396 | -do- | -do- | -do- | -do-
65 | DA Bolt 22" | Nos | 3000 | 389 | 1.167 | -do- | -do- | -do- | -do-
66 | Bolts & Nuts 5/8x2" |  | 20000 | 58.9 | 1.178 | -do- | -do- | -do- | -do-
67 | Bolts & Nuts 5/8x6" |  | 15000 | 103.257 | 1.5489 | -do- | -do- | -do- | -do-
68 | Bolts & Nuts 5/8x9" |  | 36000 | 211.1032 | 7.5997 | -do- | -do- | -do- | -do-
69 | Bolts & Nuts 5/8x12" |  | 20000 | 236.3438 | 4.7269 | -do- | -do- | -do- | -do-
70 | Bolts & Nuts 5/8x14" |  | 8200 | 316.6548 | 2.5966 | -do- | -do- | -do- | -do-
71 | R/Washer 1.75"dia,5/8"hole |  | 45000 | 114.73 | 5.1628 | -do- | -do- | -do- | -do-
Total (Distribution Material) |  |  |  |  | 14949.0178
T&P Items and Insulated Bucket Mounted Vehicles
1 | Safety Belt / Parachute Harness | Nos. | 3800 | 4595 | 17.461 | -do- | -do- | -do- | -do-
2 | Lineman Uniform (XXL) | Nos. | 500 | 4598 | 2.299 | -do- | -do- | -do- | -do-
3 | Lineman Uniform (XL) | Nos. | 3048 | 4598 | 14.0147 | -do- | -do- | -do- | -do-
4 | Lineman Uniform (L) | Nos. | 6222 | 4598 | 28.6088 | -do- | -do- | -do- | -do-
5 | Lineman Uniform (M) | Nos. | 4600 | 4598 | 21.1508 | -do- | -do- | -do- | -do-
6 | Lineman Uniform (Small) | Nos. | 540 | 4598 | 2.4829 | -do- | -do- | -do- | -do-
7 | Lineman Safety Boot Size-7 | PR | 1752 | 4297 | 7.5283 | -do- | -do- | -do- | -do-
8 | Lineman Safety Boot Size-8 | PR | 3188 | 4297 | 13.6988 | -do- | -do- | -do- | -do-
9 | Lineman Safety Boot Size-9 | PR | 1891 | 4696 | 8.8801 | -do- | -do- | -do- | -do-
10 | Lineman Safety Boot Size-10 | PR | 577 | 4699 | 2.7113 | -do- | -do- | -do- | -do-
11 | Rubber Insulating Gloves | PR | 15200 | 2724 | 41.4048 | -do- | -do- | -do- | -do-
12 | Leather Protective Gloves | PR | 14080 | 375 | 5.28 | -do- | -do- | -do- | -do-
13 | Safety Hat | Nos. | 7100 | 523 | 3.7133 | -do- | -do- | -do- | -do-
14 | Fiber Glass Ladder 36ft Ext. | Nos. | 690 | 35000 | 24.15 | -do- | -do- | -do- | -do-
15 | Fiber Glass Ladder 48ft Ext. | Nos. | 100 | 36000 | 3.6 | -do- | -do- | -do- | -do-
16 | Chain Pulley Block 5 Ton | Nos. | 230 | 23268 | 5.3516 | -do- | -do- | -do- | -do-
17 | Ratchet Lever Hoist 750 Kg | Nos. | 230 | 9100 | 2.093 | -do- | -do- | -do- | -do-
18 | Ratchet Lever Hoist 1500 Kg | Nos. | 100 | 12274 | 1.2274 | -do- | -do- | -do- | -do-
19 | Grip Pulling Cond. 6.0-10 MM | Nos. | 230 | 2450 | 0.5635 | -do- | -do- | -do- | -do-
20 | Grip Pulling Cond. 12.5-15 MM | Nos. | 100 | 4088 | 0.4088 | -do- | -do- | -do- | -do-
21 | Wrench Adjustable 200 mm | Nos. | 3800 | 310 | 1.178 | -do- | -do- | -do- | -do-
22 | Wrench Adjustable 300 mm | Nos. | 200 | 389 | 0.0778 | -do- | -do- | -do- | -do-
23 | Insulated Plier (side cutting) | Nos. | 3800 | 560 | 2.128 | -do- | -do- | -do- | -do-
24 | Hand Line | Nos. | 3800 | 1987 | 7.5506 | -do- | -do- | -do- | -do-
25 | Screw Driver 8" | Nos. | 3800 | 175 | 0.665 | -do- | -do- | -do- | -do-
26 | Bolt Cutter | Nos. | 230 | 3526 | 0.81098 | -do- | -do- | -do- | -do-
27 | Disconnect Stick | Nos. | 1200 | 3849 | 4.6188 | -do- | -do- | -do- | -do-
28 | Lineman Knife | Nos. | 3800 | 275 | 1.045 | -do- | -do- | -do- | -do-
29 | First Aid Box | Nos. | 230 | 3815 | 0.87745 | -do- | -do- | -do- | -do-
30 | Manila Rope | Mtrs. | 9200 | 306 | 2.8152 | -do- | -do- | -do- | -do-
31 | Tree Trimmer | Nos. | 200 | 1054 | 0.2108 | -do- | -do- | -do- | -do-
32 | Grounding Set | Nos. | 920 | 24764 | 22.7829 | -do- | -do- | -do- | -do-
33 | Torch 3 Cell | Nos. | 1380 | 1087 | 1.5001 | -do- | -do- | -do- | -do-
34 | Lineman Tool Bag | Nos. | 3800 | 585 | 2.223 | -do- | -do- | -do- | -do-
35 | Clip on Meter (Volt Amp) | Nos. | 400 | 5645 | 2.258 | -do- | -do- | -do- | -do-
36 | Voltage Beeper | Nos. | 3800 | 452 | 1.7176 | -do- | -do- | -do- | -do-
37 | Live Wire Tester | Nos. | 3800 | 115 | 0.437 | -do- | -do- | -do- | -do-
38 | Earth Resistance Tester | Nos. | 200 | 40242 | 8.0484 | -do- | -do- | -do- | -do-
39 | Magger 1000 V | Nos. | 0 | 0 | 0 | -do- | -do- | -do- | -do-
40 | Voltage Detector | Nos. | 200 | 19990 | 3.998 | -do- | -do- | -do- | -do-
41 | Rain Coat Size-50" | Nos. | 2539 | 2009 | 5.1009 | -do- | -do- | -do- | -do-
42 | Rain Coat Size-52" | Nos. | 3111 | 1983 | 6.1691 | -do- | -do- | -do- | -do-
43 | Rain Coat Size-54" | Nos. | 1762 | 1892 | 3.3337 | -do- | -do- | -do- | -do-
44 | Life Saving Chain | Nos. | 3800 | 1543 | 5.8634 | -do- | -do- | -do- | -do-
45 | Warning Cones 17" | Nos. | 2300 | 500 | 1.15 | -do- | -do- | -do- | -do-
46 | Warning Tapes | Nos. | 115000 | 50 | 5.75 | -do- | -do- | -do- | -do-
47 | Rubber Insulating Sleeves | Nos. | 1200 | 7511 | 9.0132 | -do- | -do- | -do- | -do-
Total (T&P / Vehicle) |  |  |  |  | 307.9511
1 | Insulated Bucket Mounted Vehicles | Nos. | 35 | 19770000 | 691.95
ABC Cables and Accessories |  |  |  |  | 263.1
Grand Total (Million Rs.) |  |  |  |  | 16212.0189